## Front End
WORKPLAN
[5 empty] | 2019-06-01 | [29 empty] | 2001-07-01
[5 empty] | Week 1 | [29 empty] | Week 1
Task Name | Start Date | End Date | Duration | Person on duty | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
Already Developed pending approval
Home page | 4th June | 5th June | 2 days | JM/JN
Footer | 4th June | 5th June | 2 days | JM/JN
Careers Page
Job Page | 4th June | 4th June | 1 day | JM/JN
Job Description | 4th June | 4th June | 1 day | JM/JN
Login Page | 4th June | 4th June | 1 day | JM/JN
Registration page | 4th June | 4th June | 1 day | JM/JN
Privacy Agreement Page | 4th June | 4th June | 1 day | JM/JN
Combined Form page | 4th June | 4th June | 1 day | JM/JN
Summary Page | 4th June | 4th June | 1 day | JM/JN
Portal Page | 4th June | 4th June | 1 day | JM/JN
Applicant Dashboard | 4th June | 4th June | 1 day | JM/JN
Applicant Job submission | 4th June | 4th June | 1 day | JM/JN
applicant profile page | 4th June | 4th June | 1 day | JM/JN
applicant recommended jobs | 4th June | 4th June | 1 day | JM/JN
HR SYSTEM | 4th June | 4th June | 1 day | JM/JN
Resgistration page | 4th June | 4th June | 1 day | JM/JN
Login page | 4th June | 4th June | 1 day | JM/JN
Landing page (dashboard) | 4th June | 4th June | 1 day | JM/JN
Create post | 4th June | 4th June | 1 day | JM/JN
preview created post | 4th June | 4th June | 1 day | JM/JN
created post pdf download | 4th June | 4th June | 1 day | JM/JN
live post | 4th June | 4th June | 1 day | JM/JN
applicant table | 4th June | 4th June | 1 day | JM/JN
applicant information details | 4th June | 4th June | 1 day | JM/JN
archive posts | 4th June | 4th June | 1 day | JM/JN
edit archive post | 4th June | 4th June | 1 day | JM/JN
preview archived posts | 4th June | 4th June | 1 day | JM/JN
archived post pdf download | 4th June | 4th June | 1 day | JM/JN
approved candidate table | 4th June | 4th June | 1 day | JM/JN
approved candidate information | 4th June | 4th June | 1 day | JM/JN
closed jobs - jobs that have passed the deadline | 4th June | 4th June | 1 day | JM/JN
approved candidates under closed jobs | 4th June | 4th June | 1 day | JM/JN
create new user | 4th June | 4th June | 1 day | JM/JN
users table | 4th June | 4th June | 1 day | JM/JN
Copy Pending
Home page -intro | 4th June | 6thJune | 2 days | JM/SK | bar: Week 1 4 to Week 1 6
Product details | 4th June | 6thJune | 2 days | JM/SK | bar: Week 1 4 to Week 1 6
Apollo Centre | 4th June | 6thJune | 2 days | BM/JM | bar: Week 1 4 to Week 1 6
Request Assistance | 4th June | 6thJune | 2 days | JM/SK | bar: Week 1 4 to Week 1 6
Log in portals | 4th June | 6thJune | 2 days | JM/SK | bar: Week 1 4 to Week 1 6
Media Centre | 4th June | 6thJune | 2 days | JM/JT | bar: Week 1 4 to Week 1 6
CSR | 4th June | 6thJune | 2 days | JM/JT | bar: Week 1 4 to Week 1 6
Checked pending corrections
Corrections and design structures | 3rd June | 3th June | 1 day | PC | bar: Week 1 3
Development of pending pages | PHASE ONE
Media Centre | 4rd June | 4th June | 1 days | PC
CSR Page | 5th June | 6th June | 2 days | PC | bar: Week 1 5 to Week 1 7
About us landing page | 10th June | 13th June | 4 days | PC | bar: Week 1 10 to Week 1 13
Company Pages | 14th june | 17th June | 2 days | PC | bar: Week 1 14 to Week 1 16
Products page |  |  | 7 days | PC
Prodcut lead forms | 18th June | 19th June | 2 days | PC | bar: Week 1 17 to Week 1 18
Contact us page | 7th June | 7th June | 2 days | PC | bar: Week 1 7
Gallery Page -Apollo Centre | 19th june | 20th June | 2 days | PC | bar: Week 1 19
Apollo Centre -Booking modal (pop up) - lead form | 20th June | 21th June | 1 days | PC | bar: Week 1 20 to Week 1 21
Mega menu | 22nd June | 22nd June | 2days | PC | bar: Week 1 21 to Week 1 22
Carousel and banner(responsiveness) | 24nd June | 24th June | 1 day | PC | bar: Week 1 24
Interlinking pages | 26th June | 26th June | 1 days | PC | bar: Week 1 25
Social media widgets (facebook, instagram , twitter) -pulling content from company accounts | 28th June | 28th June | 1 day | PC | bar: Week 1 26
site responsiveness(homepage etc) | 27th June | 27th June | 1 day | PC | bar: Week 1 27
request call modal (pop up) | 2nd July | 2nd July | 0.5 day | PC | bar: Week 1 28; Week 1 2
feedback modal | 2nd July | 2nd July | 0.5 day | PC | bar: Week 1 2
google map integration with company branches embedded | 3rd July | 5th July | 2 days | PC | bar: Week 1 3
Design of Pending pages
About us landing page | 3rd | 5th June | 3 days | PC/PK/JM | bar: Week 1 3 to Week 1 5
Company Pages | 3rd | 5th June | 3 days | PC/PK/JM | bar: Week 1 3 to Week 1 5
Products page | 3rd | 5th June | 3 days | PC/PK/JM | bar: Week 1 3 to Week 1 6
Gallery Page -Apollo Centre | 3rd | 5th June | 3 days | PC/PK/JM | bar: Week 1 3 to Week 1 6
Pop us | 3rd | 5th June | 3 days | PC/PK/JM | bar: Week 1 3 to Week 1 6
Uganda Full Site
PHASE TWO
CMS HOMEPAGE
Posting products
CRUD(create read update delete) products
products table
login + registration
lead forms
product quotation
cms - media centre
post content - CRUD
post content table
login page
create user
users table
cms - CSR
post content - CRUD
post content table
login page
create user
users table
crs - apollo centre
CRUD operations on the booked rooms
customer table
empty rooms table
booked rooms
create user
users table
login page
HR SYSTEM
Create email
inbox
ANALYTICS
google analytics
facebook pixel
KEY |  | Corrections
pending approval
Under Development
Approved
Uganda Website

## Back End Development (hidden)
WORKPLAN
[5 empty] | 2019-05-01 | [6 empty] | 2019-06-01
[5 empty] | Week 4 | [6 empty] | Week 1
Task Name | Start Date | End Date | Duration | Person on duty | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Pending Job
Already Developed pending approval
Database - applicant | 3rd june | 4th june | 1 day | JM/GN
Log In Page | 29th May | 29th May | 1 day | JM/GN
Registration page | 29th May | 29th May | 1 day | JM/GN
Forgot Password Page | 29th May | 29th May | 1 day | JM/GN
Dash board landing page | 29th May | 29th May | 1 day | JM/GN
Job Post | 29th May | 29th May | 1 day | JM/GN
API Intergration | 29th May | 29th May | 1 day | JM/GN
HR SYSTEM | PHASE ONE
database schema | 3rd june | 4th june | 1 day | GN/AB
Combined Form | 4th June | 7th June | 4th day | GN/AB
login page | 10th June | 11th June | 1 day | GN/AB
landing page (dashboard) | 11th June | 12th June | 1 day | GN/AB
create post | 12th June | 14th June | 2 days | GN/AB
preview created post | 17th June | 19th June | 2 days | GN/AB
created post pdf download | 19th June | 20th June | 1 day | GN/AB
live post | 20th June | 21th June | 2 days | GN/AB
applicant table | 12th June | 13th June | 1 day | GN/AB
applicant information details | 24th June | 25th June | 1 day | GN/AB
PHASE TWO
archive posts |  |  | 1 day | GN/AB
edit archive post |  |  | 2 days | GN/AB
preview archived posts |  |  | 1 day | GN/AB
archived post pdf download |  |  | 1 day | GN/AB
approved candidate table |  |  | 1 day | GN/AB
approved candidate information |  |  | 1 day | GN/AB
closed jobs - jobs that have passed the deadline |  |  | 2 days | GN/AB
approved candidates under closed jobs |  |  | 1 day | GN/AB
create new user |  |  | 1 day | GN/AB
users table |  |  | 1 day | GN/AB
generate password for new user and send email |  |  | 2 days | GN/AB
email notifications |  |  | 1 day | GN/AB
Apollo Centre booking Sytem | PHASE ONE
Database | 25th June | 26th June | 1 days | GN/AB
Login Page | 26th June | 27th June | 1 day | GN/AB
Dashboard | 27th June | 28th June | 1 day | GN/AB
Booked rooms | 1th July | 2th July | 1 day | GN/AB
Available Rooms | 3th July | 4th July | 1 day | GN/AB
Customer Details | 4th July | 5st July | 1 day | GN/AB
Create users | 8th July | 9th July | 1day | GN/AB
New Development
Media Centre CMS | PHASE TWO
Post creation |  |  | 1 day | GN/AB
Remove Post |  |  | 1 day | GN/AB
Log in page |  |  | 1 day | GN/AB
Registration Page |  |  | 1 day | GN/AB
Database |  |  | 1 day | GN/AB
Edit post |  |  | 1 day | GN/AB
Profile Page |  |  | 1 day | GN/AB
Create User |  |  | 1 day | GN/AB
Dashboard |  |  | 1 day | GN/AB
CSR CMS | PHASE TWO
Post creation | 13th June | 14th June | 1 day | GN/AB
Remove Post | 14th June | 15th June | 1 day | GN/AB
Log in page | 15th June | 16th June | 1 day | GN/AB
Registration Page | 16th June | 17th June | 1 day | GN/AB
Database | 17th June | 18th June | 1 day | GN/AB
Edit post | 18th June | 19th June | 1 day | GN/AB
Profile Page | 19th June | 20th June | 1 day | GN/AB
Accounts Page | 20th June | 21st June | 1 day | GN/AB
Dashboard | 21st June | 22nd June | 1 day | GN/AB
CMS HOMEPAGE | PHASE TWO
database schema |  |  | 1 day | GN/AB
CRUD(create read update delete) products |  |  | 4 days | GN/AB
products database |  |  | 1 day | GN/AB
login + registration |  |  | 1 days | GN/AB
lead forms |  |  | 1 day | GN/AB
lead table |  |  | 1 day | GN/AB
product quotation |  |  | 2 days | GN/AB

## Changes
Website Changes
1 | Nav bar to remain static when client scrolls down
2 | Logo to use -APA Insurance
3 | Add search at the top
4 | What we offer -Remove the copy at the top and remain with images only
5 | Change download PDF to Download sample policy
6 | Consistency -Change button colors - Blue -Get cover Red- Download Grey -To a further action
7 | Point the travel and marine get cover to portal
8 | Pictures -consistency in all rounded edges
9 | Link booking pop Up
10 | Log in change to portals
11 | Alignment of copy
12 | Footer
Regulated by IRA -at the middle
T&Cs to the far right
13 | About Us
Reduce white space
Add the brand promise
14 | Customer Charter
Redesign not clear
15 | Media Centre and CSR
Copy to be outside the images
16 | Report a claim -content on how to report a claim as well as claim forms
17 | Home page slider images
18 | T&C -send to legal for review

## Sheet1
WORKPLAN
[10 empty] | 2019-05-01 | [6 empty] | 2019-06-01
| F.E | B.E | D.B | COPY | PROJECT |  |  |  |  | Week 4 | [6 empty] | Week 1
Task Name | PETER CHEGE | ANTHONY BARU | GILBERT NJOROGE | JOYCE MUIRURI | PHASE | Start Date | End Date | Duration | Person on duty | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Pending Job
Tasks
HOMEPAGE |  |  |  |  | ONE
landing page | C | N/A | N/A |  | ONE |  |  | -
mega menu | NC | N/A | N/A |  | ONE |  |  | 2
carousel and banner(responsiveness) | NC | N/A | N/A |  | ONE |  |  | 1
product details | C | N/A | N/A |  | ONE |  |  | -
copy of access services | NC | N/A | N/A |  | ONE
interlinking pages | NC | N/A | N/A |  | ONE |  |  | 1
site responsiveness(homepage etc) | NC | N/A | N/A |  | ONE |  |  | 1.5
footer | C | N/A | N/A |  | ONE |  |  | -
chatbot | N/A | NC | N/A |  |  |  |  | w
cms - homepage |  |  |  |  | TWO
posting products from B.E | NC | NC | NC |  | TWO |  |  | 1
CRUD(create read update delete) products | NC | NC | NC |  | TWO |  |  | 5
products database | NC | NC | NC |  | TWO |  |  | 1
login + registration | NC | NC | NC |  | TWO |  |  | 1
database schema | NC | NC | NC |  | TWO |  |  | 0.5
lead forms | NC | NC | NC |  | TWO |  |  | 2
lead forms B.E | NC | NC | NC |  | TWO |  |  | 1
product quotation | NC | NC | NC |  | TWO |  |  | 1
PRODUCTS |  |  |  |  | ONE
landing page | C | N/A | N/A |  | ONE |  |  | w
product details | NC | NC | NC |  | ONE |  |  | w
ABOUT US | NC | N/A | N/A |  | ONE
landing page | NC | N/A | N/A |  | ONE |  |  | w
our customers service charter | NC | N/A | N/A |  | ONE |  |  | w
group companies (landing page) | NC | N/A | N/A |  | ONE |  |  | w
profile modal (pop up) | NC | N/A | N/A |  | ONE |  |  | w
APA insurance landing page | NC | N/A | N/A |  | ONE |  |  | w
APA insurance profile modal | NC | N/A | N/A |  | ONE |  |  | w
Apollo Asset Management | NC | N/A | N/A |  | ONE |  |  | w
Apollo Asset Management profile modal | NC | N/A | N/A |  | ONE |  |  | w
Gordon Court landing page | NC | N/A | N/A |  | ONE |  |  | w
MEDIA CENTRE |  |  |  |  | ONE
landing page | NC | NC | NC |  | ONE |  |  | 1
social media widgets (facebook, instagram , twitter) -pulling content from company accounts | NC | NC | NC |  | ONE |  |  | 2.5
post details | NC | NC | NC |  | ONE |  |  | 1
cms - media centre |  |  |  |  | TWO
post content - CRUD | NC | NC | NC |  | TWO |  |  | 5
post content database schema | NC | NC | NC |  | TWO |  |  | 0.5
CORPORATE SOCIAL RESPONSIBILITY(CSR) |  |  |  |  | ONE
landing page | NC | NC | NC |  | ONE |  |  | 1
post details | NC | NC | NC |  | ONE |  |  | 1
csr database schema | NC | NC | NC |  | ONE |  |  | 1
APOLLO CENTRE |  |  |  |  | ONE
landing page | NC | NC | NC |  | ONE |  |  | 1
gallery page | NC | NC | NC |  | ONE |  |  | 1
booking modal (pop up) - lead form | NC | NC | NC |  | ONE |  |  | 1
crs - apollo centre |  |  |  |  | ONE
CRUD operations on the booked rooms | NC | NC | NC |  | ONE |  |  | 4
customer database | NC | NC | NC |  | ONE |  |  | 1
customer table | NC | NC | NC |  | ONE |  |  | 0.5
booked rooms | NC | NC | NC |  | ONE |  |  | 1
CAREERS |  |  |  |  | ONE
landing page | C | N/A | N/A |  | ONE |  |  | -
job page - available jobs | C | C | N/A |  | ONE |  |  | -
job detailed description | C | C | N/A |  | ONE |  |  | -
login page | C | C | N/A |  | ONE |  |  | -
registration page | C | C | N/A |  | ONE |  |  | -
password reset page (forgot password) | C | C | N/A |  | ONE |  |  | -
social media api sign in and sign up integrations (facebook, linkedin , google) | C | C | N/A |  | ONE |  |  | -
privacy agreement | C | N/A | N/A |  | ONE |  |  | -
combined form - personal information, work history, education background, file attachment | C | N/A | NC |  | ONE |  |  | 3
application information summary | C | N/A | NC |  | ONE |  |  | 1
applicant dashboard - landing page | C | N/A | NC |  | TWO |  |  | 1
applicant job submissions | C | N/A | NC |  | TWO |  |  | 1
applicant profile page | C | N/A | NC |  | TWO |  |  | 2
applicant recommended jobs | C | N/A | NC |  | TWO |  |  | 1
HR SYSTEM
resgistration page | C | NC | NC |  | ONE |  |  | 0.5
login page | C | NC | NC |  | ONE |  |  | 0.5
landing page (dashboard) | C | NC | NC |  | ONE |  |  | 0.5
create post | C | NC | NC |  | ONE |  |  | 1
preview created post | C | NC | NC |  | ONE |  |  | 1
created post pdf download | C | NC | NC |  | ONE |  |  | 1
live post | C | NC | NC |  | ONE |  |  | 1
applicant table | C | NC | NC |  | ONE |  |  | 1
applicant information details | C | NC | NC |  | ONE |  |  | 1
archive posts | C | NC | NC |  | TWO |  |  | 1
edit archive post | C | NC | NC |  | TWO |  |  | 2
preview archived posts | C | NC | NC |  | TWO |  |  | 1
archived post pdf download | C | NC | NC |  | TWO |  |  | 2
approved candidate table | C | NC | NC |  | TWO |  |  | 2
approved candidate information | C | NC | NC |  | TWO |  |  | 1
closed jobs - jobs that have passed the deadline | C | NC | NC |  | TWO |  |  | 1
approved candidates under closed jobs | C | NC | NC |  | TWO |  |  | 1
create new user | C | NC | NC |  | TWO |  |  | 2
users table | C | NC | NC |  | TWO |  |  | 0.5
generate password for new user and send email | NC | NC | NC |  | TWO |  |  | 3
email notifications | NC | NC | NC |  | TWO |  |  | 1
CONTACT US |  |  |  |  | ONE
landing page | NC | N/A | N/A |  | ONE |  |  | 1
request call modal (pop up) | NC | N/A | N/A |  | ONE |  |  | 0.5
feedback modal | NC | N/A | N/A |  | ONE |  |  | 0.5
google map integration with company branches embedded | NC | N/A | N/A |  | ONE |  |  | 2
ONLINE SERVICES (PORTALS) |  |  |  |  | ONE
landing page | C | N/A | N/A |  | ONE |  |  | -
interlinking tabs on landing page with their respective portals | NC | N/A | N/A |  | ONE |  |  | 0.5
ANALYTICS |  |  |  |  | TWO
google analytics | NC | N/A | N/A |  | TWO |  |  | 1
facebook pixel | NC | N/A | N/A |  | TWO |  |  | 1

## Back End
WORKPLAN
[5 empty] | 2019-06-01 | [29 empty] | 2001-07-01
[5 empty] | Week 1 | [29 empty] | Week 1
Task Name | Start Date | End Date | Duration | Person on duty | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
Products page/Homepage/What we offer
lead forms |  |  | 4 | bar: Week 1 4; Week 1 6
lead forms database schema |  |  | 2 | bar: Week 1 4; Week 1 6
Lead management system | bar: Week 1 4; Week 1 6
login |  |  | 2 | bar: Week 1 4; Week 1 6
registration/create account |  |  | 2 | bar: Week 1 4; Week 1 6
dashboard leads - pending, sorted, new leads, call back, failed, pending |  |  | TBD | bar: Week 1 4; Week 1 6
leads details |  |  | TBD
new leads table |  |  | TBD
call back table |  |  | TBD
closed table |  |  | TBD
pending table |  |  | TBD
disintrested table |  |  | TBD
analytics/report generation in multiple formats |  |  | TBD
lead management system database |  |  | TBD
Apollo Centre/Homepage
website booking (F.E + B.E)
booking form |  |  | 1
Validation plus response |  |  | 1
CUSTOMER RESERVATION SYSTEM
database |  |  | C
create user |  |  | 1
email token + generation password |  |  | 1
feedbacks |  |  | 1
log in |  |  | 1
dashboard |  |  | 1
Shimba room bookings table |  |  | 1
Chyullu room bookings table |  |  | 1
Cherengani room bookings table |  |  | 1
Taita hill table |  |  | 1
Ngong hills table |  |  | 1
Entertainment area table |  |  | 1
About Us / Media centre/Csr /Download
Downloads : financial reports + trail blazers |  |  | 2
html flipbook widget |  |  | TBD
media centre landing page - pulling media centre posts to the front end of the site |  |  | C 0.5
content details for the above posts |  |  | C 0.5
pagination for media centre posts |  |  | 2
csr landing page - pulling csr posts to the front end of the site |  |  | C 0.5
content details for the above posts |  |  | C 0.5
pagination for csr posts |  |  | 2
content management system (cms)
database |  |  | C 1
forgot password |  |  | C 2
register/ email registration token |  |  | 2
log in |  |  | C
dashboard |  |  | C
pagination for the dashboard table |  |  | 2
new post |  |  | C
ck editor embedding on new post page |  |  | C
preview post |  |  | C 1
edit post |  |  | C
delete post |  |  | C
categories |  |  | C
manage admins |  |  | C
dashboard menu for financials and trailblazer |  |  | TBD
database for financials and trailblazer |  |  | 1
document posts |  |  | 1
preview document post |  |  | TBD
edit post |  |  | TBD
delete post |  |  | TBD
Careers
job post |  |  | C
job details |  |  | C
login |  |  | C
registration |  |  | C
sign and sign up with social media apis (linked, google+) |  |  | C
reset password/forgot password |  |  | C
application form / combined form |  |  | 5
summary of job applicant has applied for |  |  | 2
email notification for successful submission |  |  | 1
available jobs |  |  | 1
applied jobs with withdraw functionality |  |  | 1
account profile after successful registration or login |  |  | 3
edit profile - information obtained from combined form |  |  | 4
applicant database |  |  | C
feedback / communication |  |  | TBD
HR System/ careers cms
database schema |  |  | C
login |  |  | 1
forgot password |  |  | 0.5
email token for activating user accounts + password rest |  |  | 1
dashboard |  |  | 1
create job post |  |  | 1
embedding ckeditor5 on create job post page |  |  | C
preview post |  |  | 1
download pdf |  |  | 1
view application |  |  | 1
edit post |  |  | 1
archive post |  |  | 1
view applicants |  |  | 1
applicant details |  |  | 1
approved candidates |  |  | 1
candidate table |  |  | 1
candidate details |  |  | 1
archived posts |  |  | 1
restore post |  |  | 0.5
delete post |  |  | 0.5
create user |  |  | 1
email token for activating new user accounts + password rest |  |  | 1
applicant database |  |  | C
user/admin database |  |  | C
feedback |  |  | TBD
broadcast emails |  |  | TBD
Corrections
KEY |  | pending approval
Under Development
Approved
Uganda Website
| TBD | to be discussed